Pragmatic GRC™

IG-03
Sustain Implementation Guide — Execution Log

Operational Record | Based on Chapter 8.2, The Four Implementation Guides

Manage risk and build operational resilience.

# Document Information

| Organization | Orrville Medical Associates |
| --- | --- |
| Prepared By | Linda Foster |
| Approved By | Dr. Michael Bennett |
| Primary Living Document Supported | R-003 Enterprise Risk Register |
| Period Covered | August 12, 2026 – September 15, 2026 |
| Next Scheduled Use | Next incident, or the annual BC/DR exercise |

# 1. Trigger for This Cycle

The phishing incident (C-001) activated incident response procedures. Separately, this cycle also completed the annual backup restoration test that had been an open action item since the initial risk assessment (R-013).

# 2. Primary Objective

Orchestrate active risk treatment, maintain business continuity, run disaster recovery pipelines, and fire incident response protocols.

# 3. Key Tasks Addressed This Cycle

☑ Immediate real-time triage, containment, and eradication of active security incidents

☑ Executing independent backup data restoration validation and live data integrity tests

☐ Activating alternative, manual operational workarounds during payment gateway or cloud platform drops

☑ Driving the risk burn-down milestones and mitigation tracks managed on the executive dashboard

# 4. Participants

| Name | Role | Involvement |
| --- | --- | --- |
| Dr. Michael Bennett | Business Owner (Primary) | Directed incident response priorities |
| Linda Foster | Operations Manager (Primary) | Coordinated recovery and backup test logistics |
| Summit IT Partners | MSP (Supporting) | Executed technical containment and the backup restoration test |

# 5. Actions Taken

| Date | Action | Owner | Outcome |
| --- | --- | --- | --- |
| 08/12/2026 | Executed the incident response playbook for the phishing incident | Linda Foster / Summit IT Partners | See C-001 for the full record |
| 08/13/2026 | Incident classified as contained; not a reportable HIPAA breach | Dr. Michael Bennett | Documented in C-001, Section 8 |
| 09/15/2026 | Conducted the annual backup restoration test across the EHR, billing, and local workstation backups | Summit IT Partners | Restoration successful; R-013 residual risk confirmed at Low |
| 09/15/2026 | Updated the Risk Register with backup test results and closed the associated action item | Linda Foster | R-003 Dashboard reflects 0 open High/Critical residual risks |

# 6. Deliverables Produced

| Deliverable | Status | Reference |
| --- | --- | --- |
| Updated Business Continuity procedures | Partial | Formal BC plan not yet drafted; informal procedures documented in F-002, Section 8 |
| Disaster Recovery procedures | Complete | F-002 Backup & Recovery table (Section 7) |
| Incident Response playbooks | Complete | C-001 |
| Verified backup restoration results | Complete | Annual test completed 09/15/2026 |
| Current emergency contact lists | Complete | C-001 Contact Directory |
| Updated risk treatment activities | Complete | R-003 Risk Assessment Worksheet |
| Lessons learned from exercises or incidents | Complete | C-001, Section 10 |

# 7. Common Mistakes Checked Against

| Mistake to Avoid | Present? | Notes |
| --- | --- | --- |
| Assuming backups work without testing them | Not Present | Restoration was formally tested this cycle |
| Developing recovery plans that depend on one employee | Present | Linda Foster remains the sole administrator for most recovery coordination (see R-017) |
| Failing to define manual workarounds during outages | Present | No documented manual fallback procedure yet (see R-007) |
| Waiting until an emergency to determine responsibilities | Not Present | Roles were pre-defined in C-001 |
| Never reviewing or exercising recovery procedures | Not Present | Annual test completed this cycle |

# 8. Success Check

| Criterion | Status | Notes |
| --- | --- | --- |
| Recovery priorities are clearly documented | Met |  |
| Backup restoration has been successfully tested | Met |  |
| Incident response responsibilities are understood | Met |  |
| Manual business processes have been identified | Partially Met | See R-007 |
| Leadership can respond to a disruption without confusion or unnecessary delay | Met |  |

# 9. Next Steps / Carry-Forward Items

Identify and train a backup administrator to reduce key-person dependency (R-017); document a paper-based EHR downtime procedure (R-007).

# Related Pragmatic GRC™ Resources

• R-003 Risk Assessment Worksheet

• C-001 Incident Response Playbook

• F-002 Unified System Security Plan

• G-002 Monthly GRC Heartbeat™ Checklist