Pragmatic GRC™

IG-04
Cultivate Implementation Guide — Execution Log

Operational Record | Based on Chapter 8.2, The Four Implementation Guides

Embed compliance and governance into organizational culture.

# Document Information

| Organization | Orrville Medical Associates |
| --- | --- |
| Prepared By | Linda Foster |
| Approved By | Dr. Michael Bennett |
| Primary Living Document Supported | F-002 Unified System Security Plan |
| Period Covered | September 1, 2026 – September 7, 2026 (program launch) |
| Next Scheduled Use | Ongoing bi-weekly micro-training; reinforced at next onboarding |

# 1. Trigger for This Cycle

The corrective action tracker from the August 2026 incident (C-001, CA-001) called for formal, recurring phishing simulation training. This cycle launched that program, directly addressing the previously informal approach to security awareness (R-015).

# 2. Primary Objective

Build an enterprise human firewall, automate awareness training, map leadership steering, and scale compliance culture.

# 3. Key Tasks Addressed This Cycle

☑ Executing the under-60-minute user identity revocation and offboarding protocol

☑ Conducting routine, bi-weekly social engineering and phishing micro-quizzes inside your communication apps

☐ Embedding security checkpoints directly into the standard hiring, role-change, and exit lifecycles

☑ Transitioning corporate governance from an annual administrative event into an ongoing executive cultural reflex

# 4. Participants

| Name | Role | Involvement |
| --- | --- | --- |
| Linda Foster | HR / Program Administrator (Primary) | Designed and launched the training program |
| Dr. Michael Bennett | Business Owner (Supporting) | Endorsed the program to all staff |
| Dr. Sarah Whitfield, Amanda Cole PA-C, David Nguyen PA-C, Rachel Torres RN, Kevin Brooks LPN, Maria Gonzalez CNA, Tyler Simmons CNA, Jessica Park | All Staff (Participants) | Enrolled in the first training cycle |

# 5. Actions Taken

| Date | Action | Owner | Outcome |
| --- | --- | --- | --- |
| 09/01/2026 | Selected and enrolled all staff in a quarterly phishing simulation platform | Linda Foster | CA-001 marked Complete (see C-001) |
| 09/03/2026 | Delivered the first bi-weekly phishing micro-quiz via Microsoft Teams | Linda Foster | 9 of 10 staff completed within 48 hours |
| 09/07/2026 | Reviewed training completion and governance culture during the Monthly GRC Heartbeat™ | Linda Foster / Dr. Michael Bennett | Recorded in G-002 KPI Review (Security Training Completion) |

# 6. Deliverables Produced

| Deliverable | Status | Reference |
| --- | --- | --- |
| Updated onboarding and offboarding procedures | Partial | Formal written checklist still pending (R-005) |
| Current security awareness training records | Complete | Enrollment and completion tracked by Linda Foster |
| Role-based access reviews | Complete | Reviewed during the Monthly GRC Heartbeat™ (G-002, Section 3) |
| Governance responsibility assignments | Complete | F-002 Governance Roles table |
| Employee acknowledgment of security responsibilities | Partial | Verbal acknowledgment only; written process planned |
| Updated organizational accountability records | Complete | F-002, Section 4 |

# 7. Common Mistakes Checked Against

| Mistake to Avoid | Present? | Notes |
| --- | --- | --- |
| Treating security awareness as an annual checkbox exercise | Not Present | Program is bi-weekly/quarterly, not annual |
| Forgetting to remove user accounts immediately after termination | Present | Offboarding still relies on verbal notification (R-005) |
| Assuming employees understand governance responsibilities without training | Not Present | Formal training is now underway |
| Providing the same training regardless of job role | Present | Current program is one-size-fits-all; role-based content planned |
| Failing to reinforce good security behaviors throughout the year | Not Present | Bi-weekly cadence established |

# 8. Success Check

| Criterion | Status | Notes |
| --- | --- | --- |
| Employees understand their security responsibilities | Partially Met | Program just launched |
| New hires receive governance and security training during onboarding | Not Yet Met | No new hires since launch; process not yet formalized |
| Departing employees lose access promptly | Partially Met | See R-005 |
| Leadership demonstrates accountability for governance decisions | Met |  |
| Security awareness has become part of normal business operations rather than a once-a-year event | Met | Program established |

# 9. Next Steps / Carry-Forward Items

Formalize the written offboarding checklist (R-005); develop role-based training content; introduce written acknowledgment of security responsibilities.

# Related Pragmatic GRC™ Resources

• F-002 Unified System Security Plan

• C-001 Incident Response Playbook

• G-002 Monthly GRC Heartbeat™ Checklist

• R-003 Risk Assessment Worksheet