## Instructions
Pragmatic GRC™ — R-003 Risk Assessment Worksheet v3.0
Purpose
Use this workbook to document and evaluate individual risk scenarios before approved risks are transferred to R-001 — Enterprise Risk Register. The workbook supports consistent scoring, treatment decisions, approvals, executive review, and cross-references to F-001, F-002, R-001, and R-005.
Step | Action | Related Resource | Use
1 | Enter one risk scenario per row on the Risk Assessments sheet. | F-001 — Master Asset Register | Identify the asset, service, vendor, or business process being assessed.
2 | Select likelihood and impact using the 1–3 scale. | F-002 — Unified System Security Plan | Reference applicable controls and SSP sections.
3 | Document existing controls, then score residual likelihood and impact. | R-001 — Enterprise Risk Register | Transfer approved risks for ongoing governance and monitoring.
4 | Select a treatment strategy and assign an accountable risk owner. | R-005 — Risk Treatment Plan | Document detailed mitigation actions for risks requiring treatment.
5 | Record approval status and, when approved, transfer the risk to R-001. | G-002 — Monthly GRC Heartbeat™ | Review new, overdue, and high-risk assessments.
6 | Review outstanding assessments during the Monthly GRC Heartbeat™.

## Lookup Lists
Likelihood | Impact | Category | Treatment Strategy | Assessment Status | Approval Status | Transfer Status
1 | 1 | Strategic | Accept | Draft | Pending | Not transferred
2 | 2 | Operational | Mitigate | In Review | Approved | Transferred to R-001
3 | 3 | Cybersecurity | Transfer | Approved | Rejected | Not applicable
|  | Compliance | Avoid | Closed
|  | Financial | Monitor
Third-Party
Human
Physical
Reputational

## Scoring Guide
Risk Scoring Guide
Rating | Likelihood | Description |  | Rating | Impact | Description
1 | Low | Unlikely to occur or expected less than once every three years. |  | 1 | Low | Limited disruption; minimal financial, operational, or reputational effect.
2 | Medium | Could occur or has occurred within the last one to three years. |  | 2 | Medium | Noticeable disruption requiring management attention and recovery effort.
3 | High | Likely to occur or has occurred within the last year. |  | 3 | High | Significant disruption, major loss, regulatory exposure, or reputational harm.
Score | Rating | Interpretation | Recommended Action
1 | Low | Within normal operating tolerance. | Monitor and document controls.
2 | Low | Limited exposure. | Monitor and review periodically.
3 | Low | Manageable exposure. | Confirm controls remain effective.
4 | Medium | Requires planned action or management review. | Document treatment and owner.
5 | Medium | Meaningful exposure. | Prioritize treatment and review monthly.
6 | Medium | Material exposure. | Escalate to leadership and define treatment.
7 | High | Outside normal tolerance. | Immediate treatment and executive visibility.
8 | High | Severe exposure. | Urgent action and frequent monitoring.
9 | Critical | Unacceptable exposure. | Immediate executive action; consider avoidance.

## Risk Assessments
R-003 — Risk Assessment Worksheet
Assessment ID | Assessment Date | Assessor | Business Owner | Department | Category | Asset / Process | F-001 Asset ID | Threat | Vulnerability | Existing Controls | Likelihood | Impact | Inherent Score | Inherent Rating | Treatment Strategy | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Risk Owner | Target Date | Days Remaining | F-002 SSP Section | R-001 Risk ID | R-005 Treatment Plan | Assessment Status | Approval Status | Transfer Status | Last Review Date | Notes
RA-001 | 2026-07-01 | L. Foster | Dr. Michael Bennett | Clinical | Cybersecurity | EHR System | A-004 | Phishing-driven credential theft targeting EHR login credentials | Limited security awareness training; no simulated phishing program | MFA on Microsoft 365; EHR vendor-enforced MFA; basic annual training | 3 | 3 | 9 | Critical | Mitigate | 2 | 2 | 4 | Medium | Linda Foster | 2026-09-30 | 72 | Identity and Access Management | R-001 | TP-001 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Enroll all staff in quarterly phishing simulations.
RA-002 | 2026-07-01 | L. Foster | Linda Foster | Clinical | Cybersecurity | Nursing Workstations | A-013 | Ransomware infecting shared clinical workstations | Inconsistent endpoint detection coverage across shared nursing workstations | MSP-managed antivirus, patch management, and monitored backups | 3 | 3 | 9 | Critical | Mitigate | 2 | 2 | 4 | Medium | Linda Foster | 2026-09-30 | 72 | Security Controls | R-002 | TP-002 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Confirm EDR coverage on all three shared workstations with MSP.
RA-003 | 2026-07-01 | L. Foster | Dr. Michael Bennett | Clinical | Physical | Physician / PA Mobile Devices | A-010 | Loss or theft of a mobile device (iPhone, iPad, or laptop) containing PHI | Devices used off-site for clinical access; remote-wipe enforcement not independently verified | Device passcodes; mobile device management (MDM) enrollment | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-08-31 | 42 | Identity and Access Management | R-003 | TP-003 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Verify MDM remote-wipe is enabled and tested on all mobile devices.
RA-004 | 2026-07-01 | L. Foster | Linda Foster | Clinical | Operational | Nursing Workstations | A-013 | Unauthorized access via shared workstation logins | Shared devices increase risk of inadequate individual user accountability | Informal manual sign-in log | 3 | 2 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | Identity and Access Management | R-004 | TP-004 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Move to individual login credentials per staff member on shared stations.
RA-005 | 2026-07-01 | L. Foster | Linda Foster | Administration | Operational | Staff Offboarding | N/A | Delayed offboarding of departed staff; access not revoked timely | No formal offboarding checklist; process depends on verbal notification to the MSP | Verbal notification process to MSP upon departure | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-08-31 | 42 | Identity and Access Management | R-005 | TP-005 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Formalize written offboarding checklist covering all SaaS systems.
RA-006 | 2026-07-01 | L. Foster | Linda Foster | Administration | Third-Party | Managed Service Provider | A-020 | Overprivileged or compromised MSP remote access | Limited practice visibility into MSP internal security controls | Signed MSP services agreement; access via managed remote-support tools | 2 | 3 | 6 | Medium | Mitigate | 1 | 3 | 3 | Low | Linda Foster | 2026-10-31 | 103 | Vendor Security | R-006 | TP-006 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Request MSP security attestation and review access logs quarterly.
RA-007 | 2026-07-01 | L. Foster | Dr. Michael Bennett | Clinical | Third-Party | EHR System | A-004 | EHR vendor service outage disrupting clinical documentation | No documented downtime or paper-based fallback procedure | Vendor SLA; vendor-managed cloud redundancy | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Dr. Michael Bennett | 2026-09-30 | 72 | Backup & Recovery | R-007 | TP-007 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Document a paper-based downtime procedure for clinical staff.
RA-008 | 2026-07-01 | L. Foster | Linda Foster | Administration | Third-Party | Patient Billing System | A-006 | Data breach at patient billing SaaS vendor | Limited practice oversight of vendor security posture | Vendor Business Associate Agreement (BAA); vendor attestation requested | 2 | 3 | 6 | Medium | Transfer | 1 | 3 | 3 | Low | Linda Foster | 2026-10-31 | 103 | Vendor Security | R-008 | TP-008 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Confirm current SOC 2 report or equivalent attestation on file.
RA-009 | 2026-07-01 | L. Foster | Linda Foster | Administration | Cybersecurity | Office Wi-Fi Network | A-018 | Wireless network compromise via weak Wi-Fi configuration | Shared network configuration; encryption settings not independently verified | WPA2/3 encryption; MSP-managed router and firewall | 2 | 2 | 4 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | Security Controls | R-009 | TP-009 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Request MSP configuration review and confirm guest network segmentation.
RA-010 | 2026-07-01 | L. Foster | Linda Foster | Administration | Financial | Microsoft 365 / Email | A-001 | Business email compromise leading to a fraudulent payment request | No secondary verification process for payment or banking change requests | MFA enabled on Microsoft 365 email | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-08-31 | 42 | Security Controls | R-010 | TP-010 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Require verbal confirmation for any banking or payment detail changes.
RA-011 | 2026-07-01 | L. Foster | Linda Foster | Administration | Compliance | SaaS Vendor Contracts | N/A | Missing or expired Business Associate Agreements (BAAs) with SaaS vendors | No centralized BAA tracking process | Contracts held individually by the office manager | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | Vendor Security | R-011 | TP-011 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Build a BAA tracking log covering EHR, scheduling, billing, and MSP.
RA-012 | 2026-07-01 | L. Foster | Linda Foster | Administration | Cybersecurity | All Endpoints | N/A | Delayed patching of endpoints and network devices | Patch cadence depends entirely on MSP schedule; no independent verification | MSP-managed patch management program | 2 | 2 | 4 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | Security Controls | R-012 | TP-012 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Request monthly patch compliance report from MSP.
RA-013 | 2026-07-01 | L. Foster | Linda Foster | Administration | Operational | Backup Systems | N/A | Backup failure or unrecoverable data loss | Backup restoration has not been tested in the past 12 months | MSP-managed automated backups | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-08-31 | 42 | Backup & Recovery | R-013 | TP-013 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Schedule and document an annual backup restoration test.
RA-014 | 2026-07-01 | L. Foster | Linda Foster | Administration | Cybersecurity | Practice Website | A-007 | Practice website vulnerability exposing the scheduling integration | Website and plugin patching cadence not independently confirmed | MSP-managed website maintenance | 2 | 2 | 4 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-10-31 | 103 | Security Controls | R-014 | TP-014 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Request confirmation of website patch and vulnerability scan cadence.
RA-015 | 2026-07-01 | L. Foster | Linda Foster | Administration | Human | All Staff | N/A | Insufficient security awareness among clinical and administrative staff | Onboarding does not include documented security awareness training | Ad hoc verbal guidance from the office manager | 3 | 2 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | Governance Roles | R-015 | TP-015 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Implement documented security awareness training at onboarding and annually.
RA-016 | 2026-07-01 | L. Foster | Linda Foster | Administration | Physical | Office Facility | A-026 | Unauthorized after-hours physical access to the office | Key and access control process is not formally documented | Locked doors; alarm system | 1 | 2 | 2 | Low | Accept | 1 | 2 | 2 | Low | Linda Foster |  |  | System Boundaries | R-016 | N/A | Approved | Approved | Transferred to R-001 | 2026-07-01 | Risk accepted at current control level; revisit if facility changes.
RA-017 | 2026-07-01 | L. Foster | Linda Foster | Administration | Operational | Practice Administration | N/A | Key-person dependency: office manager is the sole administrator of critical systems | No documented cross-training or backup administrator identified | None formally documented | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Dr. Michael Bennett | 2026-10-31 | 103 | Governance Roles | R-017 | TP-017 | In Review | Pending | Not transferred | 2026-07-01 | Identify and train a backup administrator among clinical staff.
RA-018 | 2026-07-01 | L. Foster | Linda Foster | Administration | Financial | Cyber Insurance Policy | N/A | Cyber insurance coverage may be insufficient relative to potential HIPAA breach costs | Policy limits have not been benchmarked against breach-cost data | General liability policy with a basic cyber endorsement | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-11-30 | 133 | Compliance Obligations | R-018 | TP-018 | In Review | Pending | Not transferred | 2026-07-01 | Review policy limits with broker against HIPAA breach cost benchmarks.
RA-019 | 2026-07-01 | L. Foster | Linda Foster | Administration | Operational | Practice Domain Name | A-027 | Domain name expiration or unauthorized transfer disrupting the website, email, and patient scheduling access | Domain renewal is not on a tracked recurring calendar; single point of failure if registrant contact information lapses | Domain registered under practice ownership; MSP holds registrar access | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | System Boundaries | R-019 | TP-019 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Add domain renewal date to the Monthly GRC Heartbeat™ recurring checklist; confirm auto-renewal and current registrant contact information.
RA-020 | 2026-07-01 | L. Foster | Linda Foster | Administration | Operational | HIPAA-Compliant Fax Machine | A-029 | Misdirected fax transmission disclosing PHI to an unintended recipient | Fax numbers are entered manually with no independent verification step before sending | HIPAA-compliant fax cover sheet with a standard confidentiality notice | 2 | 2 | 4 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-09-30 | 72 | Security Controls | R-020 | TP-020 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Require a second-person number verification step before sending records containing PHI.
RA-021 | 2026-07-01 | L. Foster | Linda Foster | Clinical | Cybersecurity | Patient Portal | A-030 | Patient portal account takeover due to weak or reused patient passwords | Portal password requirements rely on vendor defaults; no patient-side MFA requirement | Vendor-hosted authentication; password reset via email verification | 2 | 2 | 4 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-10-31 | 103 | Identity and Access Management | R-021 | TP-021 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Confirm with the EHR vendor whether patient-side MFA can be enabled on the portal.
RA-022 | 2026-07-01 | L. Foster | Linda Foster | Administration | Compliance | PHI Records (Paper & Retired Devices) | N/A | Improper retention or disposal of PHI in paper records and retired devices | No documented data retention schedule or secure disposal procedure exists | Informal practice of shredding paper records; device disposal handled ad hoc by the MSP | 2 | 3 | 6 | Medium | Mitigate | 1 | 2 | 2 | Low | Linda Foster | 2026-10-31 | 103 | Security Controls | R-022 | TP-022 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Document a formal data retention schedule and secure disposal procedure, including certificate of destruction for retired devices.
RA-023 | 2026-07-01 | L. Foster | Linda Foster | Administration | Physical | Front Desk / Waiting Area | A-026 | Incidental disclosure of PHI through front-desk or waiting-room conversations | Check-in area layout allows conversations to be overheard; no documented physical-privacy safeguards | Staff informally lower their voices during check-in discussions | 2 | 2 | 4 | Medium | Mitigate | 1 | 1 | 1 | Low | Linda Foster | 2026-11-30 | 133 | System Boundaries | R-023 | TP-023 | Approved | Approved | Transferred to R-001 | 2026-07-01 | Add privacy signage and evaluate a sound-buffering or spacing adjustment at check-in.
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
[13 empty] | 0 | Low |  |  |  | 0 | Low
Formulas:
Days Remaining = IF([Target Date]="","",[Target Date]-TODAY())

## Dashboard
R-003 Executive Assessment Dashboard
Metric | Value | Category | Count | Treatment Strategy | Count
Total Assessments | 23 | Strategic | 0 | Accept | 1
High / Critical Inherent | 2 | Operational | 6 | Mitigate | 21
High / Critical Residual | 0 | Cybersecurity | 6 | Transfer | 1
Pending Approval | 2 | Compliance | 2 | Avoid | 0
Approved Assessments | 21 | Financial | 2 | Monitor | 0
Transferred to R-001 | 21 | Third-Party | 3
Overdue Treatments | 0 | Human | 1
|  | Physical | 3
|  | Reputational | 0

## Executive Summary
R-003 Risk Assessment Executive Summary
Summary Metric | Value |  | Governance Review Notes
Total Assessments | 23 |  | Use this space to record executive decisions, risk acceptance, treatment priorities, and follow-up actions from the governance meeting.
High / Critical Inherent | 2
High / Critical Residual | 0
Pending Approval | 2
Transferred to R-001 | 21
Overdue Treatments | 0
Approval Role | Name | Decision | Signature / Date
Assessor
Business Owner
Reviewer / Approver