Pragmatic GRC™

R-005
Risk Treatment Plan

Risk Management Resource | Version 1.0

# Document Information

| Organization | Orrville Medical Associates |
| --- | --- |
| Related Risk ID | R-001 (RA-001) |
| Treatment Plan ID | TP-001 |
| Prepared By | Linda Foster |
| Date | August 20, 2026 |
| Related Resources | R-003, F-002, C-001, IG-04, G-002 |

# Purpose

Detail the action plan for R-001 — phishing-driven credential theft targeting EHR login credentials — which earned a full treatment plan after the August 12, 2026 incident (see C-001) demonstrated this risk was not theoretical.

# 1. Risk Summary

| Field | Details |
| --- | --- |
| Risk ID (R-003) | R-001 / RA-001 |
| Risk Description | Phishing-driven credential theft targeting EHR login credentials |
| Category | Cybersecurity |
| Inherent Score / Rating | 9 / Critical |
| Target Residual Score / Rating | 4 / Medium |
| Risk Owner | Linda Foster |

# 2. Treatment Strategy

| Strategy | Selected? | Rationale |
| --- | --- | --- |
| Mitigate — reduce likelihood or impact | ☑ | MFA already reduces impact; recurring training reduces likelihood |
| Transfer — shift risk via insurance or contract | ☐ |  |
| Accept — acknowledge and monitor without further action | ☐ |  |
| Avoid — eliminate the activity causing the risk | ☐ | Not feasible — email is essential to operations |

# 3. Action Plan

| Step | Owner | Target Date | Status |
| --- | --- | --- | --- |
| Select and procure a phishing simulation platform | Linda Foster | 08/31/2026 | Complete |
| Enroll all staff in the first simulation cycle | Linda Foster | 09/01/2026 | Complete |
| Deliver bi-weekly phishing micro-quizzes via Microsoft Teams | Linda Foster | Ongoing | In Progress |
| Review training completion during the Monthly GRC Heartbeat™ | Linda Foster / Dr. Michael Bennett | Monthly | In Progress |
| Introduce role-based training content (clinical vs. administrative) | Linda Foster | 12/31/2026 | Not Started |

# 4. Resources Required

A phishing simulation platform subscription (low-cost, per-user pricing); approximately 15 minutes of staff time per bi-weekly cycle; Linda Foster's time to administer and report on the program.

# 5. Status Tracking

| Review Date | Status | Notes |
| --- | --- | --- |
| 09/07/2026 | In Progress | First micro-quiz delivered; 9 of 10 staff completed within 48 hours (see G-002) |

# 6. Approval

| Approved By | Role | Date |
| --- | --- | --- |
| Dr. Michael Bennett | Executive Sponsor | August 20, 2026 |

# Small Business Adaptation

This is one of only two risks in Orrville's register that received a full treatment plan (the other being the backup restoration test tracked under R-013). Every other risk in R-003 resolves with a single owner and a note — this one earned the extra structure because the August incident proved it was urgent, and the fix genuinely required more than one step.

🔗 Related Resources: R-003 Risk Assessment Worksheet • F-002 Unified System Security Plan • C-001 Incident Response Playbook • IG-04 Cultivate Execution Log • G-002 Monthly GRC Heartbeat™ Checklist

# Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | August 20, 2026 | Linda Foster | Initial treatment plan for R-001, following the August 2026 incident |